## Test_Plan
PARABANK CAPSTONE – TEST PLAN
Item | Details
Project Overview | Comprehensive test plan and verification framework for ParaBank's core transactions (account creation and fund transfer). This master document coordinates Robot Framework automation runs, ensuring high coverage and regression safety across UI and API layers.
Testing Objectives | • Validate account opening workflows and fund transfer screens via Selenium/Browser Library UI automation. • Verify REST API response structures, status codes, and data types (id, customerId, type, balance). • Ensure financial integrity (balance deltas and ledger entries) across UI and API transactions. • Catch boundary violations, validation bypasses, and edge-case errors through negative assertions.
Scope | • UI: Account creation, navigation, and fund transfer fields via SeleniumLibrary. • API: Account retrieval (GET) and transfer requests (POST). • E2E: UI-driven transactions validated against API ledger. • Negative/Boundary: Zero, blank, alphabetic, and overdraft amount inputs.
Application Under Test | ParaBank Demo Banking Application UI: https://parabank.parasoft.com/parabank/index.htm API: https://parabank.parasoft.com/parabank/api-docs/index.html
Test Strategy | • POM: home_page.robot, open_new_account_page.robot, transfer_funds_page.robot. • API Library: RequestsLibrary via api_keywords.robot. • Parallel Sharding: Pabot across 4 parallel processes with clean browser contexts.
Test Environment | • AUT: https://parabank.parasoft.com • Browser: Chrome (SeleniumLibrary) • Framework: Robot Framework 7+ ¦ Python 3.14 • Libraries: SeleniumLibrary, RequestsLibrary, DataDriver • Runner: Windows 10/11 & GitHub Actions CI freestyle
Entry Criteria | • AUT is online and Swagger API docs are reachable. • Robot Framework, SeleniumLibrary, RequestsLibrary, and DataDriver are installed. • Variables (CUSTOMER_ID, ACCOUNT_ID, ACCOUNT_ID_2, INVALID_ID) are configured.
Exit Criteria | • All 22 test cases fully executed and logged. • Pass rate ≥ 70% (excluding documented application bugs). • All defects logged in Defect Report sheet. • RTM confirms full coverage of all functional requirements.
Risks and Mitigation | • Demo DB resets deleting test data → Pre-run setup registers users dynamically. • Shared accounts modified by concurrent runs → Run sequentially or use unique account numbers. • API instability → Execute API tests independently and log blockers.
Deliverables | • QA Documentation: Plan, Requirements, Scenarios, Cases, RTM, Execution Log, Defects, Summary. • Robot Framework suites: UI, API, E2E, Negative. • Automation Logs: log.html, report.html, Allure report dashboards.
Functional Requirements | FR-01: Create new account via UI FR-02: GET accounts list via API FR-03: Validate new account exists in API FR-04: Validate account type and details in API FR-05: Transfer funds via UI FR-06: Validate updated balances using API FR-07: Validate transfer applied correctly (before/after values) FR-08: Validate UI messages (success, confirmation) FR-09: Validate negative / boundary scenarios
Prepared By | Shivam Dhanuka

## Functional_Requirements
FUNCTIONAL REQUIREMENTS — ParaBank Capstone
Req ID | Requirement Name | Description | Acceptance Criteria | Testing Type | Priority
FR-01 | Create New Account via UI | User shall create checking/savings accounts by selecting type and funding source via UI. | New account created; account number displayed in success banner. | UI | High
FR-02 | GET Accounts List via API | System returns all accounts for a customer ID via GET API. | HTTP 200 OK with valid JSON array containing at least one account. | API | High
FR-03 | Validate New Account Exists in API | Account created via UI must appear in GET accounts API response. | Newly created account ID present in GET /customers/{customerId}/accounts. | Hybrid | High
FR-04 | Validate Account Type and Details in API | API account details must match UI-created account data. | Response contains id, customerId, type, balance with correct values. | Hybrid | High
FR-05 | Transfer Funds via UI | User transfers funds between accounts via Transfer Funds web page. | Transfer completes; 'Transfer Complete!' message displayed. | UI | Critical
FR-06 | Validate Updated Balances via API | Balances update correctly in API ledger after a transfer. | Source debited; destination credited; GET /accounts/{id} reflects new balances. | API | Critical
FR-07 | Validate Transfer Before/After Values | Transfer amount accurately reflected in both account balances. | Balance delta equals transferred amount for both accounts. | Hybrid | Critical
FR-08 | Validate UI Success Messages | System displays confirmation messages after account creation and transfers. | 'Account Opened!' after creation; 'Transfer Complete!' after transfer. | UI | Medium
FR-09 | Validate Negative / Boundary Scenarios | System rejects invalid inputs: zero, blank, alphabetic, overdraft, invalid IDs. | Invalid actions blocked; appropriate error responses returned. | UI/API | High

## Test_Scenarios
TEST SCENARIOS — ParaBank Capstone
Scenario ID | Module / Feature | Scenario Title | Type | Objective | Expected Result | Linked Req(s) | Priority
TS-01 | Account Opening UI | Account Provisioning UI Operations | UI | Validate navigation links and checking/savings account creation via Open New Account page. | Pages load correctly; accounts created; success banners display valid account numbers. | FR-01, FR-08 | High
TS-02 | Funds Transfer UI | Valid Fund Transfer Execution via UI | UI | Validate fund transfer of a positive amount between accounts via Transfer Funds page. | Transfer completes; 'Transfer Complete!' confirmation displayed. | FR-05, FR-08 | High
TS-03 | UI Negative / Boundary | UI Form Boundary and Validation Testing | UI | Confirm zero, blank, alphabetic, and overdraft amount inputs are properly handled. | Zero/overdraft blocked; blank/alpha inputs trigger server error message. | FR-09 | High
TS-04 | Account API Queries | Customer Account API Ledger Queries | API | Validate GET endpoints for customer accounts list and specific account details. | HTTP 200 OK; correct JSON schema; all required fields present. | FR-02, FR-03, FR-04 | High
TS-05 | Funds Transfer API | REST API Fund Transfers and Transaction Tracking | API | Validate POST transfer execution, balance debit/credit, and transaction ledger entries. | Transfer processed; balances updated; Debit/Credit entries in transaction history. | FR-06, FR-07 | High
TS-06 | API Error Handling | API Boundary and Error Response Validation | API | Confirm correct error handling for invalid account IDs and overdraft transfer attempts. | API returns non-200 for overdraft; invalid ID request handled gracefully. | FR-09 | High
TS-07 | E2E Hybrid Flow | E2E Account Provisioning and API Validation | E2E | Create savings account via UI and verify account ID, type, and existence via API. | Account created via UI; API confirms SAVINGS type and correct account ID. | FR-01,FR-02,FR-03,FR-04,FR-08 | Critical
TS-08 | E2E Hybrid Flow | E2E Fund Transfer UI and API Transaction Audit | E2E | Transfer $120 via UI and confirm Credit transaction entry in API transaction history. | 'Transfer Complete!' shown; API transaction history contains Credit entry for 120. | FR-05,FR-06,FR-07,FR-08 | Critical

## Test_Cases
TEST CASES — ParaBank Capstone (Robot Framework)
Scenario ID | Test Case ID | Test Case Name | Description | Pre-conditions | Test Steps (Robot Framework) | Expected Result
UI Based Test Cases (TC-NAV-UI-01 → TC-TX-UI-05)
TS-01 | TC-NAV-UI-01 | Verify Navigation Flow and Menu Link Integrity | Verify 'Open New Account' and 'Transfer Funds' links load correct pages from main dashboard. | Suite Setup: Load Environment Test Setup: Open Application And Login Test Teardown: Close Application Resources: common_keywords.robot, home_page.robot | 1. Open Application And Login 2. Click Open New Account 3. Sleep 1s 4. Location Should Contain 'openaccount' 5. Click Transfer Funds 6. Sleep 1s 7. Location Should Contain 'transfer' | URL contains 'openaccount' after step 4; URL contains 'transfer' after step 7. Both pages load successfully.
TS-01 | TC-AC-UI-01 | Create Savings Account with Specific Source Funding Account | Verify user can create a Savings account by selecting account type index 1 and a specific source account. | Suite Setup: Load Environment Test Setup: Open Application And Login Test Teardown: Close Application Resources: common_keywords.robot, home_page.robot, open_new_account_page.robot Env Var: ACCOUNT_ID must be set | 1. Open Application And Login 2. Click Open New Account 3. Sleep 1s 4. Location Should Contain 'openaccount' 5. Select Account Type (index=1 → SAVINGS) 6. Select Account ID from dropdown 7. Sleep 1s 8. Click Open Account Button 9. Page Should Contain 'Account Opened!' 10. Page Should Contain 'Your new account number' | Page contains 'Account Opened!' and 'Your new account number' — Savings account created successfully.
TS-01 | TC-AC-UI-02 | Create Checking Account with Default Funding Options | Verify user can create a Checking account using default pre-populated account type and source. | Suite Setup: Load Environment Test Setup: Open Application And Login Test Teardown: Close Application Resources: common_keywords.robot, home_page.robot, open_new_account_page.robot | 1. Open Application And Login 2. Click Open New Account 3. Sleep 1s 4. Location Should Contain 'openaccount' 5. Select Account Type (index=0 → CHECKING) 6. Sleep 1s 7. Click Open Account Button 8. Page Should Contain 'Account Opened!' 9. Page Should Contain 'Your new account number' | Page contains 'Account Opened!' and 'Your new account number' — Checking account created successfully.
TS-01 | TC-AC-UI-03 | Navigate to Account Details Page via Confirmation Banner Link | Verify clicking the new account number hyperlink in the success banner redirects to Account Details page. | Suite Setup: Load Environment Test Setup: Open Application And Login Test Teardown: Close Application Resources: common_keywords.robot, home_page.robot, open_new_account_page.robot | 1. Open Application And Login 2. Click Open New Account 3. Select Account Type (index=0 → CHECKING) 4. Click Open Account Button 5. Page Should Contain 'Account Opened!' and 'Your new account number' 6. Click Account Details Link 7. Sleep 1s 8. Page Should Contain 'Account Details' 9. Location Should Contain 'activity.htm?id=' | Redirected to Account Details page; URL contains 'activity.htm?id='; page contains 'Account Details'.
TS-01 | TC-AC-UI-04 | Verify Open New Account Form Controls Are Visible | Verify account type dropdown, account ID dropdown, and submit button are all visible on Open New Account page. | Suite Setup: Load Environment Test Setup: Open Application And Login Test Teardown: Close Application Resources: common_keywords.robot, home_page.robot, open_new_account_page.robot Vars: ACCOUNT_TYPE_DROPDOWN, ACCOUNT_ID_DROPDOWN, OPEN_ACCOUNT_BUTTON defined | 1. Open Application And Login 2. Click Open New Account 3. Sleep 1s 4. Location Should Contain 'openaccount' 5. Element Should Be Visible: ${ACCOUNT_TYPE_DROPDOWN} 6. Element Should Be Visible: ${ACCOUNT_ID_DROPDOWN} 7. Element Should Be Visible: ${OPEN_ACCOUNT_BUTTON} | All three form controls (account type dropdown, account ID dropdown, open account button) are visible.
TS-02 | TC-TX-UI-01 | Execute Fund Transfer of $250 Between Accounts via UI | Verify user can transfer $250 from ACCOUNT_ID to ACCOUNT_ID_2 via Transfer Funds page. | Suite Setup: Load Environment Test Setup: Open Application And Login Test Teardown: Close Application Resources: common_keywords.robot, home_page.robot, transfer_funds_page.robot, transfer_funds_variables.robot Env Vars: ACCOUNT_ID, ACCOUNT_ID_2, AMOUNT_FIELD | 1. Open Application And Login 2. Click Transfer Funds 3. Sleep 1s 4. Location Should Contain 'transfer' 5. Wait Until Element Is Visible ${AMOUNT_FIELD} (10s) 6. Input Text ${AMOUNT_FIELD} = 250 7. Wait Until Page Contains Element ${FROM_ACCOUNT_DROPDOWN} (10s) 8. Select From List By Value ${FROM_ACCOUNT_DROPDOWN} = ${ACCOUNT_ID} 9. Wait Until Page Contains Element ${TO_ACCOUNT_DROPDOWN} (10s) 10. Select From List By Value ${TO_ACCOUNT_DROPDOWN} = ${ACCOUNT_ID_2} 11. Click Transfer Button 12. Sleep 2s 13. Page Should Contain 'Transfer Complete!' | 'Transfer Complete!' displayed — $250 successfully transferred from ACCOUNT_ID to ACCOUNT_ID_2.
TS-03 | TC-TX-UI-02 | Verify Zero Amount Transfer Is Rejected [BUG-001] | Verify entering amount=0 does NOT result in a successful transfer. [FAIL — Bug exists: zero transfer is processed] | Suite Setup: Load Environment Test Setup: Open Application And Login Test Teardown: Close Application Resources: common_keywords.robot, home_page.robot, transfer_funds_page.robot, transfer_funds_variables.robot Env Vars: ACCOUNT_ID, ACCOUNT_ID_2, AMOUNT_FIELD | 1. Open Application And Login 2. Click Transfer Funds 3. Sleep 1s 4. Location Should Contain 'transfer' 5. Wait Until Element Is Visible ${AMOUNT_FIELD} (10s) 6. Input Text ${AMOUNT_FIELD} = 0 7. Select From List By Value ${FROM_ACCOUNT_DROPDOWN} = ${ACCOUNT_ID} 8. Select From List By Value ${TO_ACCOUNT_DROPDOWN} = ${ACCOUNT_ID_2} 9. Click Transfer Button 10. Sleep 2s 11. Page Should NOT Contain 'Transfer Complete!' | [EXPECTED] Page should NOT show 'Transfer Complete!' — zero amount must be blocked. [ACTUAL — BUG-001] 'Transfer Complete!' IS displayed; zero amount transfer processed without validation.
TS-03 | TC-TX-UI-03 | Verify Blank Amount Transfer Returns Server Error | Verify submitting with blank amount field results in a server error message (not a successful transfer). | Suite Setup: Load Environment Test Setup: Open Application And Login Test Teardown: Close Application Resources: common_keywords.robot, home_page.robot, transfer_funds_page.robot, transfer_funds_variables.robot Env Vars: ACCOUNT_ID, ACCOUNT_ID_2 | 1. Open Application And Login 2. Click Transfer Funds 3. Sleep 1s 4. Location Should Contain 'transfer' 5. [Amount field left blank — no input] 6. Wait Until Page Contains Element ${FROM_ACCOUNT_DROPDOWN} (10s) 7. Select From List By Value ${FROM_ACCOUNT_DROPDOWN} = ${ACCOUNT_ID} 8. Select From List By Value ${TO_ACCOUNT_DROPDOWN} = ${ACCOUNT_ID_2} 9. Click Transfer Button 10. Sleep 2s 11. Page Should Contain 'An internal error has occurred and has been logged.' | Page displays 'An internal error has occurred and has been logged.' — assertion PASSES. Transfer Complete is not shown.
TS-03 | TC-TX-UI-04 | Verify Alphabetic Amount Input Returns Server Error | Verify entering 'abc' in the amount field results in a server error message (not a successful transfer). | Suite Setup: Load Environment Test Setup: Open Application And Login Test Teardown: Close Application Resources: common_keywords.robot, home_page.robot, transfer_funds_page.robot, transfer_funds_variables.robot Env Vars: ACCOUNT_ID, ACCOUNT_ID_2, AMOUNT_FIELD | 1. Open Application And Login 2. Click Transfer Funds 3. Sleep 1s 4. Location Should Contain 'transfer' 5. Input Text ${AMOUNT_FIELD} = 'abc' 6. Wait Until Page Contains Element ${FROM_ACCOUNT_DROPDOWN} (10s) 7. Select From List By Value ${FROM_ACCOUNT_DROPDOWN} = ${ACCOUNT_ID} 8. Select From List By Value ${TO_ACCOUNT_DROPDOWN} = ${ACCOUNT_ID_2} 9. Click Transfer Button 10. Sleep 2s 11. Page Should Contain 'An internal error has occurred and has been logged.' | Page displays 'An internal error has occurred and has been logged.' — assertion PASSES. Transfer Complete is not shown.
TS-03 | TC-TX-UI-05 | Verify Excessive Amount Transfer Is Rejected [BUG-002] | Verify entering amount=100,000,000 does NOT result in a successful transfer. [FAIL — Bug exists: overdraft is processed] | Suite Setup: Load Environment Test Setup: Open Application And Login Test Teardown: Close Application Resources: common_keywords.robot, home_page.robot, transfer_funds_page.robot, transfer_funds_variables.robot Env Vars: ACCOUNT_ID, ACCOUNT_ID_2, AMOUNT_FIELD | 1. Open Application And Login 2. Click Transfer Funds 3. Sleep 1s 4. Location Should Contain 'transfer' 5. Input Text ${AMOUNT_FIELD} = 100000000 6. Wait Until Page Contains Element ${FROM_ACCOUNT_DROPDOWN} (10s) 7. Select From List By Value ${FROM_ACCOUNT_DROPDOWN} = ${ACCOUNT_ID} 8. Select From List By Value ${TO_ACCOUNT_DROPDOWN} = ${ACCOUNT_ID_2} 9. Click Transfer Button 10. Sleep 2s 11. Page Should NOT Contain 'Transfer Complete!' | [EXPECTED] Page should NOT show 'Transfer Complete!' — overdraft must be blocked. [ACTUAL — BUG-002] 'Transfer Complete!' IS displayed; excessive amount processed without balance validation.
API Based Test Cases (TC-API-01 → TC-API-10)
TS-04 | TC-API-01 | Verify GET Customer Accounts List Returns Valid Response | Verify GET /customers/{CUSTOMER_ID}/accounts returns HTTP 200 with a non-empty JSON array. | Suite Setup: Load Environment Resources: common_keywords.robot Env Var: CUSTOMER_ID | 1. Load Environment (Suite Setup) 2. Get Customer Accounts (${CUSTOMER_ID}) 3. Verify Response Code = 200 4. Set Variable body = response.json() 5. Should Not Be Empty: ${body} 6. Log To Console: ${body} | HTTP 200 OK; response JSON body is not empty and contains at least one account object.
TS-04 | TC-API-02 | Verify GET Specific Account Details Returns Correct Schema | Verify GET /accounts/{ACCOUNT_ID_2} returns HTTP 200 and response contains id, customerId, type, balance. | Suite Setup: Load Environment Resources: common_keywords.robot Env Var: ACCOUNT_ID_2 | 1. Load Environment (Suite Setup) 2. Get Account Details (${ACCOUNT_ID_2}) 3. Verify Response Code = 200 4. Should Contain response.text: 'id' 5. Should Contain response.text: 'customerId' 6. Should Contain response.text: 'type' 7. Should Contain response.text: 'balance' 8. Log To Console: response.json() | HTTP 200 OK; response text contains 'id', 'customerId', 'type', 'balance'.
TS-04 | TC-API-03 | Verify Newly Created Account Exists in Customer Accounts List | Verify ACCOUNT_ID_2 is present in GET /customers/{CUSTOMER_ID}/accounts response. | Suite Setup: Load Environment Resources: common_keywords.robot Env Vars: CUSTOMER_ID, ACCOUNT_ID_2 | 1. Load Environment (Suite Setup) 2. Get Customer Accounts (${CUSTOMER_ID}) 3. Verify Response Code = 200 4. Should Contain response.text: '${ACCOUNT_ID_2}' | HTTP 200 OK; response text contains ACCOUNT_ID_2 value — account exists in customer's account list.
TS-05 | TC-API-04 | Execute Fund Transfer via REST API — Amount $150 | Verify POST /transfer from ACCOUNT_ID to ACCOUNT_ID_2 (amount=150) returns HTTP 200 and success message. | Suite Setup: Load Environment Resources: common_keywords.robot Env Vars: ACCOUNT_ID, ACCOUNT_ID_2 with sufficient balance | 1. Load Environment (Suite Setup) 2. Transfer Funds API (${ACCOUNT_ID}, ${ACCOUNT_ID_2}, 150) 3. Verify Response Code = 200 4. Should Contain response.text: 'Successfully transferred' | HTTP 200 OK; response contains 'Successfully transferred' — $150 API transfer processed.
TS-05 | TC-API-05 | Verify Source Account Balance Is Debited After API Transfer | Verify GET /accounts/{ACCOUNT_ID} returns HTTP 200 with 'balance' field after the TC-API-04 transfer. | Suite Setup: Load Environment Resources: common_keywords.robot Env Var: ACCOUNT_ID Pre-req: TC-API-04 must have completed | 1. Load Environment (Suite Setup) 2. Get Account Details (${ACCOUNT_ID}) 3. Verify Response Code = 200 4. Should Contain response.text: 'balance' | HTTP 200 OK; response contains 'balance' field — source account details retrievable post-transfer.
TS-05 | TC-API-06 | Verify Destination Account Balance Is Credited After API Transfer | Verify GET /accounts/{ACCOUNT_ID_2} returns HTTP 200 with 'balance' field after the TC-API-04 transfer. | Suite Setup: Load Environment Resources: common_keywords.robot Env Var: ACCOUNT_ID_2 Pre-req: TC-API-04 must have completed | 1. Load Environment (Suite Setup) 2. Get Account Details (${ACCOUNT_ID_2}) 3. Verify Response Code = 200 4. Should Contain response.text: 'balance' | HTTP 200 OK; response contains 'balance' field — destination account details retrievable post-transfer.
TS-05 | TC-API-07 | Verify Source Account Transaction History Contains Debit Entry | Verify GET /accounts/{ACCOUNT_ID}/transactions returns HTTP 200 with a 'Debit' entry. | Suite Setup: Load Environment Resources: common_keywords.robot Env Var: ACCOUNT_ID Pre-req: TC-API-04 must have completed | 1. Load Environment (Suite Setup) 2. Get Account Transactions (${ACCOUNT_ID}) 3. Verify Response Code = 200 4. Should Contain response.text: 'Debit' | HTTP 200 OK; response text contains 'Debit' — debit transaction logged for source account.
TS-06 | TC-API-08 | Verify GET Account Details Handles Non-Existent Account ID | Verify GET /accounts/{INVALID_ID} request is handled (no assertion on status — logs actual response for observation). | Suite Setup: Load Environment Resources: common_keywords.robot Env Var: INVALID_ID (e.g., non-existent account value) | 1. Load Environment (Suite Setup) 2. Log To Console 'Testing non-existent account ID — expects error response' 3. Get Account Details (${INVALID_ID}) 4. [No status code assertion — actual response logged to console] | Test completes without Robot Framework assertion error. Actual API response is logged for review. (Expected HTTP 404; actual response varies.)
TS-06 | TC-API-09 | Verify POST Transfer Fails for Amount Exceeding Balance [BUG-003] | Verify POST /transfer with amount=999999 returns non-200 status code. [FAIL — Bug: overdraft allowed via API] | Suite Setup: Load Environment Resources: common_keywords.robot Env Vars: ACCOUNT_ID, ACCOUNT_ID_2 Source balance must be < 999999 | 1. Load Environment (Suite Setup) 2. Transfer Funds API (${ACCOUNT_ID}, ${ACCOUNT_ID_2}, 999999) 3. Should Not Be Equal As Integers response.status_code = 200 | [EXPECTED] Status code != 200 — overdraft transfer must be rejected. [ACTUAL — BUG-003] Status code = 200; overdraft processed; negative balance created in source account.
TS-05 | TC-API-10 | Verify Destination Account Transaction History Contains Credit Entry | Verify GET /accounts/{ACCOUNT_ID_2}/transactions returns HTTP 200 with a 'Credit' entry. | Suite Setup: Load Environment Resources: common_keywords.robot Env Var: ACCOUNT_ID_2 Pre-req: TC-API-04 must have completed | 1. Load Environment (Suite Setup) 2. Get Account Transactions (${ACCOUNT_ID_2}) 3. Verify Response Code = 200 4. Should Contain response.text: 'Credit' | HTTP 200 OK; response text contains 'Credit' — credit transaction logged for destination account.
UI + API (Hybrid / E2E) Based Test Cases (TC-E2E-01 → TC-E2E-02)
TS-07 | TC-E2E-01 | End-to-End Account Provisioning and API Validation | Create Savings account via UI, capture new account number, then verify via GET API. | Suite Setup: Load Environment Test Setup: Open Application And Login Test Teardown: Close Application Resources: common_keywords.robot, api_keywords.robot, open_new_account_page.robot, home_page.robot | 1. Open Application And Login 2. Click Open New Account 3. Sleep 1s 4. Select Account Type (index=1 → SAVINGS) 5. Click Open Account Button 6. Get New Account Number → ${account_id} 7. Get Account Details (${account_id}) via API 8. Verify Response Code = 200 9. Should Contain response.text: '${account_id}' 10. Should Contain response.text: 'SAVINGS' | HTTP 200 OK from API; response contains new account_id and type 'SAVINGS' — UI creation confirmed in API ledger.
TS-08 | TC-E2E-02 | End-to-End Fund Transfer via UI and API Transaction Audit | Transfer $120 via Transfer Funds UI, then validate Credit entry in API transaction history. | Suite Setup: Load Environment Test Setup: Open Application And Login Test Teardown: Close Application Resources: common_keywords.robot, api_keywords.robot, home_page.robot, transfer_funds_page.robot Env Vars: ACCOUNT_ID, ACCOUNT_ID_2, FROM_ACCOUNT_DROPDOWN, TO_ACCOUNT_DROPDOWN | 1. Open Application And Login 2. Click Transfer Funds 3. Enter Amount = 120 4. Wait Until Page Contains Element ${FROM_ACCOUNT_DROPDOWN} (10s) 5. Select From Account = ${ACCOUNT_ID} 6. Wait Until Page Contains Element ${TO_ACCOUNT_DROPDOWN} (10s) 7. Select To Account = ${ACCOUNT_ID_2} 8. Click Transfer Button 9. Page Should Contain 'Transfer Complete!' 10. Get Account Transactions (${ACCOUNT_ID_2}) via API 11. Verify Response Code = 200 12. Should Contain response.text: '120' | UI shows 'Transfer Complete!'; API GET /transactions returns HTTP 200 containing '120' — credit transaction confirmed for ACCOUNT_ID_2.

## RTM
REQUIREMENTS TRACEABILITY MATRIX (RTM) — ParaBank Capstone
Requirement ID | Requirement Name | Scenario ID(s) | Test Case ID(s) | Coverage Status
FR-01 | Create new account via UI | TS-01, TS-07 | TC-AC-UI-01, TC-AC-UI-02, TC-AC-UI-03, TC-E2E-01 | Covered
FR-02 | GET accounts list via API | TS-04, TS-07 | TC-API-01, TC-E2E-01 | Covered
FR-03 | Validate new account exists in API | TS-04, TS-07 | TC-API-03, TC-E2E-01 | Covered
FR-04 | Validate account type and details in API | TS-04, TS-07 | TC-API-02, TC-E2E-01 | Covered
FR-05 | Transfer funds via UI | TS-02, TS-08 | TC-TX-UI-01, TC-E2E-02 | Covered
FR-06 | Validate updated balances via API | TS-05, TS-08 | TC-API-04, TC-API-05, TC-API-06, TC-E2E-02 | Covered
FR-07 | Validate transfer before/after values | TS-05, TS-08 | TC-API-07, TC-API-10, TC-E2E-02 | Covered
FR-08 | Validate UI success messages | TS-01, TS-02, TS-07, TS-08 | TC-NAV-UI-01, TC-AC-UI-01, TC-AC-UI-02, TC-AC-UI-03, TC-TX-UI-01, TC-E2E-01, TC-E2E-02 | Covered
FR-09 | Validate negative / boundary scenarios | TS-03, TS-06 | TC-TX-UI-02, TC-TX-UI-03, TC-TX-UI-04, TC-TX-UI-05, TC-API-08, TC-API-09 | Covered — 3 open defects: BUG-001 (TC-TX-UI-02), BUG-002 (TC-TX-UI-05), BUG-003 (TC-API-09)

## Test_Execution
TEST EXECUTION RUN LOG — ParaBank Capstone (Robot Framework)
Project | ParaBank Capstone – QA Documentation
Executed By | Shivam Dhanuka
Execution Date | 17 June 2026
Environment | https://parabank.parasoft.com ¦ Python 3.14 ¦ Robot Framework 7+
Result Summary | Total: 22 ¦ Pass: 18 ¦ Fail: 4 ¦ Pass Rate: 81.8%
UI Based Test Cases
Test Case ID | Test Case Name | Exec Time | Defect ID | Evidence | Status
TC-NAV-UI-01 | Verify Navigation Flow and Menu Link Integrity | 1.8s | — | https://drive.google.com/file/d/1ZMrelgQGDmajTo9pv1kEsKIpQwK-DaSW/view?usp=drive_link https://drive.google.com/file/d/1XxXTHpgjDFLz9nqY31tjU0wAKKAj3nO9/view?usp=drive_link | Pass
TC-AC-UI-01 | Create Savings Account with Specific Source Funding | 5.2s | — | https://drive.google.com/file/d/1VrSl6M9qCKTEP-kawJNPyg9qi3n_zyEt/view?usp=sharing | Pass
TC-AC-UI-02 | Create Checking Account with Default Funding Options | 4.9s | — | https://drive.google.com/file/d/1fZ6vAV_JPhud_XpUUI3h3V4sM4IJ2aco/view?usp=drive_link | Pass
TC-AC-UI-03 | Navigate to Account Details via Confirmation Banner | 3.1s | — | https://drive.google.com/file/d/1Xx7f4qTRc14EVX_ghEQtmQNPKypNl-ST/view?usp=drive_link | Pass
TC-AC-UI-04 | Verify Open New Account Form Controls Are Visible | 2.1s | — | https://drive.google.com/file/d/1rIOQyatRzPhOj7E_7kflS3Vl2zr1qbfw/view?usp=drive_link | Pass
TC-TX-UI-01 | Execute Fund Transfer of $250 Between Accounts | 6.4s | — | https://drive.google.com/file/d/141sDQTMEFhSz7IVHMmUq4S3mW2hVvHd0/view?usp=drive_link | Pass
TC-TX-UI-02 | Verify Zero Amount Transfer Is Rejected | 2.3s | BUG-001 | https://drive.google.com/file/d/1rCdc43pWgoQEkyGe8Aq0TGllDUp0D61C/view?usp=drive_link | Fail
TC-TX-UI-03 | Verify Blank Amount Transfer Returns Server Error | 2.6s | — | https://drive.google.com/file/d/11l2A3m_5GllmOqQOxLcJpPE0ggdptEvt/view?usp=drive_link | Pass
TC-TX-UI-04 | Verify Alphabetic Amount Input Returns Server Error | 2.1s | — | https://drive.google.com/file/d/1kS_Sa_ibQePskaczmsQvwdxS9e8E55NS/view?usp=drive_link | Pass
TC-TX-UI-05 | Verify Excessive Amount Transfer Is Rejected | 7.5s | BUG-002 | https://drive.google.com/file/d/1JRbug_bWssTRfK2CYyBDRlgCkQwLnnsD/view?usp=drive_link | Fail
API Based Test Cases
Test Case ID | Test Case Name | Exec Time | Defect ID | Evidence | Status
TC-API-01 | Verify GET Customer Accounts List Returns Valid Response | 850ms | — | https://drive.google.com/drive/folders/1LyXz0K9bUp40QaYvqaP0Q9hH2U0n8M8A?usp=drive_link | Pass
TC-API-02 | Verify GET Specific Account Details Returns Correct Schema | 520ms | — | https://drive.google.com/drive/folders/1LyXz0K9bUp40QaYvqaP0Q9hH2U0n8M8A?usp=drive_link | Pass
TC-API-03 | Verify Newly Created Account Exists in Customer Accounts List | 1.1s | — | https://drive.google.com/drive/folders/1LyXz0K9bUp40QaYvqaP0Q9hH2U0n8M8A?usp=drive_link | Pass
TC-API-04 | Execute Fund Transfer via REST API — Amount $150 | 1.2s | — | https://drive.google.com/drive/folders/1LyXz0K9bUp40QaYvqaP0Q9hH2U0n8M8A?usp=drive_link | Pass
TC-API-05 | Verify Source Account Balance Is Debited After API Transfer | 490ms | — | https://drive.google.com/drive/folders/1LyXz0K9bUp40QaYvqaP0Q9hH2U0n8M8A?usp=drive_link | Pass
TC-API-06 | Verify Destination Account Balance Is Credited After Transfer | 510ms | — | https://drive.google.com/drive/folders/1LyXz0K9bUp40QaYvqaP0Q9hH2U0n8M8A?usp=drive_link | Pass
TC-API-07 | Verify Source Account Transaction History — Debit Entry | 680ms | — | https://drive.google.com/drive/folders/1LyXz0K9bUp40QaYvqaP0Q9hH2U0n8M8A?usp=drive_link | Pass
TC-API-08 | Verify GET Account Details Handles Non-Existent Account ID | 350ms | — | https://drive.google.com/drive/folders/1LyXz0K9bUp40QaYvqaP0Q9hH2U0n8M8A?usp=drive_link | Fail
TC-API-09 | Verify POST Transfer Fails for Amount Exceeding Balance | 880ms | BUG-003 | https://drive.google.com/drive/folders/1LyXz0K9bUp40QaYvqaP0Q9hH2U0n8M8A?usp=drive_link | Fail
TC-API-10 | Verify Destination Account Transaction History — Credit Entry | 680ms | — | https://drive.google.com/drive/folders/1LyXz0K9bUp40QaYvqaP0Q9hH2U0n8M8A?usp=drive_link | Pass
UI + API (Hybrid / E2E) Based Test Cases
Test Case ID | Test Case Name | Exec Time | Defect ID | Evidence | Status
TC-E2E-01 | End-to-End Account Provisioning and API Validation | 11.4s | — | https://drive.google.com/file/d/1RVxYRLjwUWIlEemKgilXgvDU1BijWrKS/view?usp=drive_link https://drive.google.com/drive/folders/1LyXz0K9bUp40QaYvqaP0Q9hH2U0n8M8A?usp=drive_link | Pass
TC-E2E-02 | End-to-End Fund Transfer via UI and API Transaction Audit | 14.2s | — | https://drive.google.com/file/d/1QyvVAlSKLZfvGgtf7zgy6t45nFdii9MN/view?usp=drive_link https://drive.google.com/drive/folders/1LyXz0K9bUp40QaYvqaP0Q9hH2U0n8M8A?usp=drive_link | Pass

## Defect_Report
DEFECT REPORT — ParaBank Capstone
Defect ID | Test Case ID | Req ID | Defect Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status
BUG-001 | TC-TX-UI-02 | FR-09 | UI processes zero amount transfer — Page Should NOT Contain 'Transfer Complete!' assertion fails. | 1. Navigate to Transfer Funds. 2. Enter 0 in the Amount field. 3. Select source and destination accounts. 4. Click Transfer. | Zero amount transfer blocked; 'Transfer Complete!' NOT displayed; validation error shown. | 'Transfer Complete!' IS displayed — zero amount ($0.00) transfer processed without validation. | Medium | Medium | Open
BUG-002 | TC-TX-UI-05 | FR-09 | UI processes overdraft transfer (100,000,000) — Page Should NOT Contain 'Transfer Complete!' assertion fails. | 1. Navigate to Transfer Funds. 2. Enter 100000000 in the Amount field. 3. Select source and destination accounts. 4. Click Transfer. | Overdraft transfer blocked; 'Transfer Complete!' NOT displayed; insufficient funds error shown. | 'Transfer Complete!' IS displayed — excessive overdraft amount processed without balance validation. | High | High | Open
BUG-003 | TC-API-09 | FR-09 | POST /transfer processes overdraft (999999) returning HTTP 200 — Should Not Be Equal As Integers assertion fails. | 1. Send POST /transfer with fromAccountId=${ACCOUNT_ID}, toAccountId=${ACCOUNT_ID_2}, amount=999999. 2. Observe HTTP status code. | HTTP status code != 200 — overdraft transfer rejected; source balance unchanged. | HTTP 200 OK returned — overdraft processed via API; source account balance goes negative. | High | High | Open

## Test_Summary_Report
FINAL TEST SUMMARY REPORT — ParaBank Capstone (Robot Framework)
PROJECT | ParaBank Capstone – QA Documentation
AUTHOR | Shivam Dhanuka
DATE | June 2026
OBJECTIVE | Validate end-to-end banking workflows (account creation, fund transfer, API validation, negative/boundary scenarios, data-driven registration, and API performance) using Robot Framework + Python across UI, API, Hybrid, Data-Driven, and Performance test layers.
EXECUTION SUMMARY
Total Test Cases Designed | 22
Total Test Cases Executed | 22
Passed | 18
Failed | 4
Blocked / Skipped | 0
Pass Rate | 81.8% (18 / 22)
Overall Status | CONDITIONAL PASS
TEST TYPE BREAKDOWN
UI Tests | 10 Executed — 8 Passed, 2 Failed (TC-TX-UI-02, TC-TX-UI-05)
API Tests | 10 Executed — 8 Passed, 2 Failed (TC-API-08, TC-API-09)
E2E / Hybrid Tests | 2 Executed — 2 Passed
Total | 22 Executed — 18 Passed, 4 Failed
REQUIREMENTS COVERAGE
Total FRs | 9 (FR-01 to FR-09)
Coverage Status | 100% — All 9 FRs covered by at least one test case across UI, API, and E2E.
FR-09 (Negative) Note | 6 negative TCs executed. 3 Pass (TC-API-08, TC-TX-UI-03, TC-TX-UI-04 return expected server error). 3 Fail: TC-TX-UI-02 → BUG-001; TC-TX-UI-05 → BUG-002; TC-API-09 → BUG-003.
DEFECTS SUMMARY
Total Open Defects | 3
Critical Severity | 0
High Severity | 2 — BUG-002 (TC-TX-UI-05: UI overdraft), BUG-003 (TC-API-09: API overdraft)
Medium Severity | 1 — BUG-001 (TC-TX-UI-02: UI zero amount transfer)
Low Severity | 0
ROBOT FRAMEWORK RESOURCES
POM Resources | home_page.robot, open_new_account_page.robot, transfer_funds_page.robot
Keyword Resources | common_keywords.robot, api_keywords.robot
Variable Resources | transfer_funds_variables.robot, environment.yaml
Libraries | SeleniumLibrary, RequestsLibrary
AUTOMATION FRAMEWORK
Framework | Robot Framework 7+ + Python 3.14
Execution Pattern | POM + API Fixtures + Parallel Execution (Pabot — 4 workers)
Browsers | Chrome (SeleniumLibrary)
Retries | 1 retry on failure
CI/CD Pipeline | GitHub Actions (.github/workflows/robot.yml)
Reports | Robot Framework HTML + Allure Report
SIGN-OFF RECOMMENDATION
Status | CONDITIONAL APPROVAL
Recommendation | 18 of 22 test cases pass (81.8%). Core functional flows — account creation, navigation, API retrieval, E2E transfer validation — are all STABLE and PASSING. Release is NOT recommended until the following 3 defects are resolved: • BUG-001 (Medium): TC-TX-UI-02 — UI allows zero amount transfers without validation. • BUG-002 (High): TC-TX-UI-05 — UI allows overdraft transfers without balance check. • BUG-003 (High): TC-API-09 — API POST /transfer allows overdraft (returns HTTP 200). Note: TC-API-08 also FAILS — GET /accounts/{INVALID_ID} does not return expected HTTP 404. This is a known application behaviour (returns HTTP 200 with empty body). Once all issues are fixed and re-tested, full release approval is recommended.